Chingu Demographic Explorer Project Plan

Business Requirement: Develop an application to display, filter, and map demographic information about Chingu members, enhancing accessibility and replacing traditional documentation with an interactive AI chat agent.

Target Tier: Full-Stack (Tier 3) implementation, including dedicated frontend and backend services.

1. Project Architecture and Technology Stack

The application uses a standard Client-Server Architecture with a dedicated API layer to manage data access and complex filtering logic. The AI agent interaction is proxied through the backend for secure API key management.

| Component | Technology | Rationale |
| --- | --- | --- |
| Frontend (Client) | React, Angular, or Vue.js (e.g., React) | Provides robust component-based UI for complex screens (Map, List) and handles state management for the shared search component. |
| Styling | Tailwind CSS or similar framework | Allows for rapid, responsive, and unique styling as required by the brief. |
| Backend (API) | Node.js with Express | Lightweight, scalable API to handle data requests, complex filtering queries, and securely proxy the Gemini API calls. |
| Database | MongoDB (NoSQL) | Highly flexible schema is ideal for storing varied Chingu demographic data (Solo Project Tier, Role, Voyage, etc.) which may have inconsistent or evolving fields. |
| Mapping | Leaflet.js (or MapBox) | A free, open-source mapping library suitable for displaying aggregated country-level data (pins). |
| AI Agent | Google Gemini API (gemini-2.5-flash-preview-09-2025) | Required tool for the optional (but highly recommended) documentation-replacement chat feature. |

2. Data Flow Diagram

The diagram illustrates the flow for core data display and the separate path for the AI chat function.

A. Core Data Flow (Map & List Screens)

- Database (MongoDB): Stores raw Chingu demographic data.

- Backend API (Node/Express):

  - Exposes secure endpoints (e.g., /api/chingus, /api/countries).

  - Receives filter parameters from the Frontend.

  - Constructs and executes complex database queries (e.g., filtering by Role, Gender, Year).

  - For the Map screen, it performs an aggregation query to count Chingus per country.

- Frontend (React App):

  - Displays the Shared Search Component.

  - Submits filter queries to the Backend on "Submit" click.

  - Receives JSON data and renders it:

    - Map Screen: Renders country pins based on aggregated counts.

    - List Screen: Renders detailed row data in a table format.

B. AI Chat Flow

- Frontend (React App): User clicks the Chat Icon, opens the Popup Dialog, and submits a question.

- Backend API Proxy:

  - Receives the user's question and conversation history.

  - Securely accesses the stored VITE_GEMINI_API_KEY.

  - Constructs the Gemini API call payload, including the system instruction/context (containing information about the app's functionality, filtering options, and structure).

- External Service (Gemini API): Processes the request and returns the AI-generated response.

- Frontend (React App): Displays the AI response in the conversation display area.

3. User Stories and Prioritization

These stories define the required functionality from the user's perspective.

Core Functionality (MVP)

| ID | User Story | Priority | Screen(s) |
| --- | --- | --- | --- |
| US-1 | As a user, I want a Home Screen that clearly explains the app's purpose and benefits so I know what the app can do. | High | Home |
| US-2 | As a user, I want a Header with clear navigation (Home, Map, List) and the current date so I can move between sections easily. | High | All |
| US-3 | As a user, I want a persistent Footer that links to the GitHub repo and lists the team members for accountability and reference. | High | All |
| US-4 | As a user, I want a Shared Search Component on the Map and List screens to filter results by various demographic attributes (Gender, Role, Country, etc.). | High | Map, List |
| US-5 | As a user, I want to submit the filter criteria to instantly update the displayed map pins or list data. | High | Map, List |
| US-6 | As a user, I want to clear the filter fields to refresh the Map screen to all data, or the List screen to the first page of all data. | High | Map, List |
| US-7 | As a user, I want the Map Screen to display geographic pins showing the aggregated count of Chingus in each country. | High | Map |
| US-8 | As a user, I want to click a country pin to see a popup listing the details of Chingus in that country, filtered by any active search criteria. | High | Map |
| US-9 | As a user, I want the List Screen to show detailed attributes (Timestamp, Gender, Country, Role, Tier, etc.) in a clear, paginated list. | High | List |
| US-10 | As a user, I want to be notified of input errors (e.g., invalid attribute values) immediately and have the error cleared once fixed. | High | All |

Stretch Goal (Optional/Recommended)

| ID | User Story | Priority | Feature |
| --- | --- | --- | --- |
| US-11 | As a user, I want a Chat Icon that opens an AI dialog so I can ask questions about the app's features instead of reading documentation. | Medium | AI Chat |
| US-12 | As a user, I want the AI agent to answer specific questions about filtering or repo usage based on the app's context. | Medium | AI Chat |

4. Project Timeline (Agile Sprints)

This timeline is structured for a 4-week development cycle, assuming a dedicated team.

| Sprint | Duration | Focus Areas | Key Deliverables (User Stories) |
| --- | --- | --- | --- |
| Sprint 1: Setup & Core UI | 1 Week | Project setup (Repo, CI/CD), Database schema, Core API endpoints, Base UI components, Styling foundation. | US-1, US-2, US-3 (Home, Header, Footer). Basic /api/chingus endpoint. Completed Database Model. |
| Sprint 2: List & Search Logic | 1 Week | Implement the shared search component logic, filtering, and the List screen data display. | US-4, US-5, US-6 (Shared Search logic). US-9 (List Screen display). Basic US-10 (Error Handling). |
| Sprint 3: Mapping & Interactivity | 1 Week | Integrate the mapping library, implement data aggregation for pins, and create the pin click popup functionality. | US-7 (Map Pins). US-8 (Pin Popup). Backend Aggregation logic. Full US-10 coverage. |
| Sprint 4: AI Integration & Polish | 1 Week | Implement the optional AI chat feature, conduct comprehensive testing, and apply final styling for distinctiveness and accessibility. | US-11, US-12 (AI Chat Pop-up and Gemini integration). Cross-browser and mobile responsiveness checks. |